## AAW NATIONAL (PANDA)
Maintenance - PO's & Outstanding Maintenance Issues
Job Complete + Invoice Received |  |  | Awaiting RN Return
Job Complete + Waiting for Invoice |  |  | Sent to RN awaiting authorisation
Job on hold |  |  | Authorised - pending completion
Ongoing Work |  |  | PAUSED - pending lease/ 2nd quote
PO | ORIGINATOR | DATE | STORE | BRAND | TICKET NO. | JOB DESCRIPTION | Notes | QUOTE OVER £200 | AUTHORISED | DATE COMPLETED | No. of days taken to resolve | INVOICE NO. | INVOICE SIGNED | INVOICE AMOUNT (EX VAT) | NOMINAL CODE
PS0308
PS0309
PS0310

## STORE MAINTENANCE
Maintenance - PO's & Outstanding Maintenance Issues
Job Complete + Invoice Received |  |  | Awaiting RN Return
Job Complete + Waiting for Invoice |  |  | Sent to RN awaiting authorisation
Ongoing Work |  |  | Authorised - pending completion
Job on hold |  |  | PAUSED - pending lease/ 2nd quote
PO | ORIGINATOR | DATE | STORE | BRAND | TICKET NO. | JOB DESCRIPTION | Notes | QUOTE OVER £200 | AUTHORISED | DATE COMPLETED | INVOICE NO. | INVOICE SIGNED | INVOICE AMOUNT (EX VAT) | NOMINAL CODE
SM0935 | SB | 2025-08-21 | Lakeside | Menkind | 112975 | Floor trim damaged (Orginally AAW - PS0307) | Engineer attending 29/08 @ 8am Engineer attending 25/10 @ 9pm | 833.94 | RN 02/09 |  | INV26790 INV27927 | 2025-12-03 | £190.05 £694.95 | 7820
SM0936 | SB | 2026-01-14 | Worcester | Menkind | Email from RN | Sparking light to be removed | Attending 14/01 | [6 empty] | 7820

## CJL
Maintenance - PO's & Outstanding Maintenance Issues
Job Complete + Invoice Received |  |  | Awaiting RN Return
Job Complete + Waiting for Invoice |  |  | Sent to RN awaiting authorisation
Job on hold |  |  | Authorised - pending completion
Ongoing Work |  |  | PAUSED - pending lease/ 2nd quote
PO | ORIGINATOR | DATE | STORE | Brand | TICKET NO. | JOB DESCRIPTION | Notes | QUOTE OVER £200 (excl VAT) | AUTHORISED | DATE COMPLETED | No. of days taken to resolve | INVOICE NO. | INVOICE SIGNED | INVOICE AMOUNT (EX VAT) | NOMINAL CODE
CJL408 | SB | 2026-01-05 | Lakeside | Menkind | 120804 | No hot water | Awaiting attendance date | 240.7 | SB 06/01 |  |  | 29558 | 2026-02-02 | 240.7 | 7820
CJL412 | SB | 2026-01-21 | Oxford | Menkind | 121497 | Door stuck in place | Awaiting attendance date | 313.95 | RN 29/01 |  |  | 29616 | 2026-02-02 | 313.95 | 7820

## OTHER
Maintenance - PO's & Outstanding Maintenance Issues
Job Complete + Invoice Received |  |  | Awaiting RN Return
Job Complete + Waiting for Invoice |  |  | Sent to RN awaiting authorisation
Ongoing Work |  |  | Authorised - pending completion
PO | ORIGINATOR | DATE | STORE | BRAND | TICKET NO. | COMPANY NAME | JOB DESCRIPTION | Notes | QUOTE OVER £200 | AUTHORISED | DATE COMPLETED | INVOICE NO. | INVOICE SIGNED | INVOICE AMOUNT (EX VAT) | NOMINAL CODE
OT0369 | SB | 2025-11-14 | Guildford | Menkind | 118568 | Maxwell Jones | Faulty front sign | Attend site and change driver in fascia sign 100w/12v |  |  |  | 37712/1383 | 2025-12-10 | 1010 | 7820
OT0363 | SB | 2025-11-21 | Taunton | Menkind | 118951 | SunBelt Rentals | 2x 3kw Fan Heater 240V Delivery: 25/11/25 Offhire: 29/12/2025 | Delivery: 25/11/2025 Collection: 07/01/2026 |  | RN 21/11 |  | 28439487 | 2025-12-15 | 69.9 | 7800
OT0361 | SB | 2025-11-03 | Lakeside | Menkind | 117549 | Metsafe | Broken safe key |  |  |  |  | 57741 | 2025-12-10 | 218 | 7800
OT0348 | SB | 2025-09-10 | Southampton | Menkind | 114465 | iLux | Damaged porthole led strip ligths | Awaiting attendance date |  |  |  | SI-3276 | 2025-12-09 | 820 | 7820

## ORDERS
Maintenance - PO's & Store Orders
Job Complete + Invoice Received
Job Complete + Waiting for Invoice
Ongoing Work
PO | ORIGINATOR | DATE | STORE | BRAND | TICKET NO. | ORDER DETAILS | SUPPLIER | QUOTE OVER £200 | AUTHORISED | DATE COMPLETED | INVOICE NO. | INVOICE SIGNED | INVOICE AMOUNT (EX VAT) | NOMINAL CODE
ORD959 | SB | 2026-01-27 | Portsmouth | Menkind | 121747 | Philips master TL-D super 80 70w/840 - QTY 1 | Lampshop Online |  |  |  | 578354 | 2026-02-02 | 26.62 | 7820
ORD957 | SB | 2026-01-23 | Cardiff | Menkind | 121661 | 6x CMH-T G12 bulbs 6x CMH-TC G8.5 3x 26W Biax-T/E | Lampshop Online |  |  |  | 577608 | 2026-02-02 | 131.34 | 7820
ORD960
ORD961
ORD962
ORD963
ORD964
ORD965
ORD966
ORD967
ORD968
ORD969
ORD970
ORD971
ORD972
ORD973
ORD974
ORD975
ORD976
ORD977
ORD978
ORD979
ORD980
ORD981
ORD982
ORD983
ORD984
ORD985
ORD986
ORD987
ORD988
ORD989
ORD990
ORD991
ORD992
ORD993
ORD994
ORD995
ORD996
ORD997
ORD998
ORD999
ORD1000

## Outstanding quotes
Store | Works | Supplier | Cost | PO | Invoice no. | Date received | Urgent or System Deficiency / Non-compliant

## AURA AC
Maintenance - PO's & Outstanding Maintenance Issues
Job Complete + Invoice Received |  |  | Awaiting RN Return
Job Complete + Waiting for Invoice |  |  | Sent to RN awaiting authorisation
Ongoing Work |  |  | Authorised - pending completion
PO | ORIGINATOR | DATE | STORE | BRAND | TICKET NO. | JOB DESCRIPTION | Notes | QUOTE OVER £200 | AUTHORISED | DATE COMPLETED | INVOICE NO. | INVOICE SIGNED | INVOICE AMOUNT (EX VAT) | NOMINAL CODE
AA0090 | [13 empty] | 7800
AA0091 | [13 empty] | 7800
AA0092 | [13 empty] | 7800
AA0093 | [13 empty] | 7800
AA0094 | [13 empty] | 7800
AA0095 | [13 empty] | 7800
AA0096 | [13 empty] | 7800
AA0097 | [13 empty] | 7800
AA0098 | [13 empty] | 7800
AA0099 | [13 empty] | 7800
AA0100 | [13 empty] | 7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800
7800

## APS
Maintenance - PO's & Outstanding Maintenance Issues
Job Complete + Invoice Received
Job Complete + Waiting for Invoice
Job on hold
Ongoing Work
PO | ORIGINATOR | DATE | STORE | BRAND | TICKET NO. | JOB DESCRIPTION | Notes | QUOTE OVER £200 | AUTHORISED | DATE COMPLETED | INVOICE NO. | INVOICE SIGNED | INVOICE AMOUNT (EX VAT) | NOMINAL CODE
APS0008
APS0009
APS0010
APS0011
APS0012
APS0013
APS0014
APS0015
APS0016
APS0017
APS0018
APS0019
APS0020
APS0021
APS0022
APS0023
APS0024
APS0025
APS0026
APS0027

## CODES
Retail Support's Nominal Code List
Travel |  |  | Supplier / Company | Code
Description | Example/Notes | Code | Lamp Shop Online | 7820
Field Management | Rob & Satellite Managers | 7400 | APS - annual service | 7800
Stock Takes |  | 7420 | APS - installation of alarm | 7830
Head Office | Jess Doyle usually books. | 7430 | Compco | 7800
Store Support | Staff cover | 7450 | MetSafe - installation | 7830
Temp Store Opening |  | 7460 | MetSafe - removal | 7840
Temp Store Closing |  | 7470 | MetSafe - replacement keys | 7800
|  |  | HASAW - FRA / PATs | 7830
Maintenance |  |  | AAW Maintenance | 7820
Description | Example/Notes | Code | Store Maintenance | 7820
Maintenance Contracts | Servicing, contracts etc. | 7800 | CJL Maintenance | 7820
Cleaning | Windows, floors etc. | 7810 | Aura Air Conditioning | 7800
Store Repairs | Reactive, bulbs etc. | 7820 | Love your Logo | 7070
|  |  | PDC Corp | 7070
Openings / Closures
Description | Example/Notes | Code
Packaging | Closure labels | 6120
Temp store consumables | Phones, ladders, extinguishers etc. | 7570
Temp store set-up costs | Safe install etc. | 7830
Temp store closedowns | Safe removal etc. | 7840
Refits (CAPEX) | Refits / Maintenance replacements >2k | 0040
Consumables
Description | Example/Notes | Code
Point of Purchase | POS Holders | 6310
Uniform | T-shirts & Name Badges | 7070
Stores | Store monthly consumables | 7530
Head Office | Paper, envelopes etc. | 7550
Recruitment
Agency (Temps) |  | 7020
Staff Training |  | 7050
Perm Recruitment & Indeed |  | 7080
Other
Description | Example/Notes | Code
Computer | FreshDesk - £280 quarterly / 5 licenses | 7720
Telephone | Focus / Chalvington etc. | 7520

## AAW PIVOT
Sum of INVOICE AMOUNT (EX VAT) | Column Labels
| 7820 |  |  |  |  | 7820 Total | Grand Total
Row Labels | 2024-06-14 | 2024-07-05 | 2024-08-02 | (blank) | 2024-06-16
Bromley | 641.08 |  |  |  |  | 641.08 | 641.08
Chelmsford
Clarks Village |  |  |  | 47.2 |  | 47.2 | 47.2
Colchester | 219.68 |  |  |  |  | 219.68 | 219.68
Eastbourne |  |  |  |  | 173.92 | 173.92 | 173.92
Guildford | 46.2 |  |  |  |  | 46.2 | 46.2
Maidstone
Southampton |  | 68.2 |  |  |  | 68.2 | 68.2
Warrington
Bracknell
Peterborough |  |  | 116.58 |  |  | 116.58 | 116.58
Grand Total | 906.96 | 68.2 | 116.58 | 47.2 | 173.92 | 1312.86 | 1312.86

## CJL PIVOT
Sum of INVOICE AMOUNT (EX VAT) | Column Labels
| 7820 | [17 empty] | 7820 Total | (blank) | (blank) Total | Grand Total
Row Labels | 02/08/2024 | 30/04/2024 08/05/2024 | 2024-04-06 | 2024-04-26 | 2024-05-08 | 2024-05-14 | 2024-07-17 | 2024-08-02 | 2024-08-14 | 2024-08-23 | (blank) | 26/04/2024 23/08/2024 30/10/2024 | 2024-12-04 | 2024-06-26 | 2024-09-23 | 2024-09-21 | 2024-10-03 | 2024-10-15 |  | (blank)
Bluewater Lower | [13 empty] | 0 |  |  |  |  | 0 |  |  | 0
Bluewater Upper | 0 | [17 empty] | 0 |  |  | 0
Brighton |  |  | 2024-04-26: 826.95 | [8 empty] | 826.95 |  |  | 826.95
Bristol | [17 empty] | 407.9 | 407.9 |  |  | 407.9
Cambridge | [15 empty] | 298.95 |  |  | 298.95 |  |  | 298.95
Cardiff |  | 0 | 2024-08-02: 291.75 | [8 empty] | 291.75 |  |  | 291.75
Chelmsford |  |  | 2024-08-14: 162; 2024-08-23: 434.2 | [8 empty] | 596.2 |  |  | 596.2
Clarks Village
Dundee
Edinburgh Fort
Gatehead |  |  | 2024-08-14: 758.7 | [8 empty] | 758.7 |  |  | 758.7
Glasgow Braehead
Glasgow Silverbur |  |  | 2024-08-14: 282 | [8 empty] | 282 |  |  | 282
Glasgow Silverburn
Hanley
Hereford
High Wycombe |  |  | 2024-08-14: 196.9 | [8 empty] | 196.9 |  |  | 196.9
Hull
Leicester | [16 empty] | 218.95 |  | 218.95 |  |  | 218.95
Liverpool | [11 empty] | 0 | 536.7 |  |  | 164.8 |  |  | 701.5 |  |  | 701.5
Livingston |  |  | 2024-08-14: 406.8 | [5 empty] | 468.95 |  |  | 875.75 |  |  | 875.75
Meadowhall |  |  | 2024-04-06: 1137 | [8 empty] | 1137 |  |  | 1137
Merry Hill | [12 empty] | 139.6 | [5 empty] | 139.6 |  |  | 139.6
Newcastle |  |  | 2024-05-08: 647 |  |  |  | 168.95 |  |  |  |  | 815.95 |  |  | 815.95
Nottingham |  |  | 2024-07-17: 191.8 | [8 empty] | 191.8 |  |  | 191.8
Peterborough
Stratford |  |  | 2024-05-14: 1129.8; 2024-08-14: 396.8 | [8 empty] | 1526.6 |  |  | 1526.6
Trafford | [14 empty] | 213.9 |  |  |  | 213.9 |  |  | 213.9
Warrington | [15 empty] | 168.9 |  |  | 168.9 |  |  | 168.9
Grand Total | 0 | 0 | 1137 | 826.95 | 647 | 1129.8 | 191.8 | 291.75 | 2203.2 | 434.2 |  | 0 | 676.3 | 168.95 | 213.9 | 1101.6 | 218.95 | 407.9 | 9649.3 |  |  | 9649.3

## OTHER PIVOT
Sum of INVOICE AMOUNT (EX VAT) | Column Labels
| 7800 | [7 empty] | 7800 Total | 7820 | [20 empty] | 7820 Total | (blank) | (blank) Total | 7830 |  | 7830 Total | 7520 |  | 7520 Total | Grand Total
Row Labels | 2024-07-12 | 2024-08-02 | (blank) | 2024-09-23 | 2024-10-07 | 2024-12-10 | 2024-09-21 | 2024-10-20 |  | 04/06/2024 | 2024-04-30 | 2024-06-03 | 2024-06-11 | 2024-07-05 | 2024-07-12 | 2024-07-17 | 2024-07-30 | 2024-08-16 | 2024-08-23 | (blank) | 2024-10-13 | 2024-10-06 | 14/08/2024 21/09/2024 03/10/2024 08/10/2024 | 2024-10-03 | 2024-09-20 | 2024-10-08 | 2024-10-11 | 04/12/2024 29/01/2025 | 2024-01-29 | 29/01/2024 |  | (blank) |  | (blank) | 2024-10-11 |  | (blank) | 2024-12-04
Blackpool |  | 294 | [6 empty] | 294 | [30 empty] | 294
Blackpool | 192 | [6 empty] | 246 | 438 | [30 empty] | 438
Bluewater U
Braehead |  |  |  | 475 |  |  |  |  | 475 | [30 empty] | 475
Brighton | [10 empty] | 2024-07-30: 1083.07 | [11 empty] | 1083.07 | [8 empty] | 1083.07
Bromley | [10 empty] | 2024-04-30: 460 | [11 empty] | 460 | [8 empty] | 460
Cambridge
Colchester | [6 empty] | 190 |  | 190 | [30 empty] | 190
Dundee | [19 empty] | 0 |  |  |  |  | 490 | [5 empty] | 490 | [8 empty] | 490
G Buchanan
Glasgow Braehead | [22 empty] | 0 | [7 empty] | 0 | [8 empty] | 0
Guildford |  | 280 | [6 empty] | 280 | [30 empty] | 280
Hanley | [23 empty] | 1270.04 | [6 empty] | 1270.04 | [8 empty] | 1270.04
Hull | [10 empty] | 2024-04-30: 120; 2024-07-12: 1661.54 | [11 empty] | 1781.54 | [8 empty] | 1781.54
Lakeside | [9 empty] | 0 | [20 empty] | 0 | [8 empty] | 0
Leeds White Rose | [20 empty] | 455 | [9 empty] | 455 | [8 empty] | 455
Leicester | [10 empty] | 2024-06-11: 71; 2024-08-16: 453.44 | [11 empty] | 524.44 | [8 empty] | 524.44
Livingston
Livingstone
Milton Keynes | [21 empty] | 1900 | [8 empty] | 1900 | [8 empty] | 1900
Nottingham
Oxford | [22 empty] | 0 | [7 empty] | 0 | [8 empty] | 0
Peterborough | [10 empty] | 2024-07-17: 1100 | [11 empty] | 1100 | [8 empty] | 1100
Portsmouth | [5 empty] | 671 |  |  | 671 | [30 empty] | 671
Reading |  |  |  |  | 638 |  |  |  | 638 | [30 empty] | 638
Silverburn | [37 empty] | 1379.87 | 1379.87 | 1379.87
Staines | [10 empty] | 2024-08-23: 1047.86 | [11 empty] | 1047.86 | [8 empty] | 1047.86
Stratford
Trafford | [10 empty] | 2024-06-03: 495; 2024-07-05: 168 | [11 empty] | 663 | [8 empty] | 663
Warehouse
(blank)
Liverpool | [24 empty] | 1421.8 | [5 empty] | 1421.8 | [8 empty] | 1421.8
Newcastle | [7 empty] | 199 | 199 | [30 empty] | 199
Derby PB | [25 empty] | 448 | 350 |  |  |  | 798 | [8 empty] | 798
Liverpool | [7 empty] | 190 | 190 | [30 empty] | 190
Birmingham | [34 empty] | 225 | 225 |  |  |  | 225
Bluewater PB | [19 empty] | 400 | [10 empty] | 400 | [8 empty] | 400
Redditch,
Guildford PB
Redditch | [27 empty] | 0 |  |  | 0 | [8 empty] | 0
Glasgow Braehead | [27 empty] | 0 |  |  | 0 | [8 empty] | 0
Edinburgh | [28 empty] | 0 |  | 0 | [8 empty] | 0
Glasgow Fort
Doncaster | [36 empty] | 250 |  | 250 | 250
Eastbourne | [29 empty] | 0 | 0 | [8 empty] | 0
Glasgow St Enoch
Cribbs
Clarks Village
Birmingham
Watford
Cwmbran
Grand Total | 192 | 574 |  | 475 | 638 | 671 | 190 | 635 | 3375 | 0 | 580 | 495 | 71 | 168 | 1661.54 | 1100 | 1083.07 | 453.44 | 1047.86 | 400 | 455 | 1900 | 0 | 1270.04 | 1911.8 | 448 | 350 | 0 | 0 | 0 | 13394.75 |  |  |  | 225 | 225 | 250 | 1379.87 | 1629.87 | 18624.62